|  | GPLA Curriculum Plan 2015 – 2017 |  |  |  |
| --- | --- | --- | --- | --- |
| Implementation and internal progress monitoring |  | GLENMORE PARK LEARNING ALLIANCE |  |  |

| Strategic direction 3: Curriculum |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project leaders: Kaylene McCormick(GPHS)+ Catherine McCann-Smith (SCPS) Carol Frith(EPPS) |  |  |  |  | Off track Implementation delayed On track |  |  |  |  |
| 2015 | TERM 1 |  | TERM 2 |  |  | TERM 3 |  | TERM 4 |  |
| PROCESS | MID TERM | END TERM | MID TERM | END TERM |  | MID TERM | END TERM | MID TERM | END TERM |
| Enter the key milestones to monitor and track delivery of the outcomes |  |  |  |  |  |  |  |  |  |
| Professional learning in each curriculum area by utilising expertise of members of the learning alliance, including TeachMeets and joint parent/community workshops. | Curriculum team committee formed across the GPLA | Create an expertise register across the GPLA Update the contact person @ each school to Professional learning via email and website calendar(Brad) | Planning of Parent Maths Forum for term 3 (personnel,flier,venue,time, food etc) Finalise History Units and shared resources | Survey for term 4 PL session formulated using Survey Monkey |  | Joint parent/carer workshop (Maths) to coincide with Education/Numeracy Week Survey results re PL needs distributed to schools PL planning for Term 4 | Finalise the arrangements and development of Geography inservice |  | 2016: Deliver 2 professional learning sessions based on current teacher needs/wants |
|  |  |  |  |  |  |  |  |  |  |
| Continue to strengthen links with Pre School and ES1 Stage 3 and Stage 4 | TOWN training across stages 3 and 4 Data analysis of numeracy continuum stages 2,3 and 4(with GPHS and feeder schools) | Maths teaching observations Stage 4 |  | Maths teaching observations Stage 4 Consistency with Aspects 4 and 5, (Place Value Multiplication and Division) Information sharing with GPHS |  | Consistency with Aspects 4 and 5, (Place Value Multiplication and Division) Information sharing with GPHS | Maths teaching observations Stage 4 Consistency with Aspects 4 and 5, (Place Value Multiplication and Division) Information sharing with GPHS | Consistency with Aspects 4 and 5, (Place Value Multiplication and Division) Information sharing with GPHS | Maths teaching observations Stage 4 |
| Enter the evaluation activity for this period |  |  |  |  |  |  |  |  |  |
| [Establish a plan to evaluate Effectiveness] |  |  |  |  |  |  |  |  | Outcomes 2015 |
| Identify the resources required to achieve the above milestones |  |  |  |  |  |  |  |  |  |
| [Monitor efficient and effective use of resources] |  |  |  |  |  |  |  |  | Outcomes 2015 |